## Experiment Log
Exp ID | Opportunity | Assumption Being Tested | Risk Type | Hypothesis | Method | Success Criteria | Start Date | End Date | Status | Result | Key Learning | Next Action | Evidence IDs
EXP-1 | Reduce status meeting prep time | PMs will trust an auto-generated status summary enough to skip manual assembly | Value | If we show PMs an AI-generated project status summary using their real task data, 4 of 5 will rate it 'accurate enough to send to my VP' without editing. | Prototype test (5 users) | 4 of 5 participants rate summary as 'send-ready' without edits | 2025-04-01 | 2025-04-15 | Completed | Invalidated | 3 of 5 said they would need to edit significantly. Main issue: the summary missed context about WHY tasks were delayed, not just THAT they were delayed. | Pivot: test version that pulls Slack context alongside task data | E1, E3
EXP-2 | Reduce status meeting prep time | PMs spend 30+ min/week on status assembly (not just a minor annoyance) | Value | If we survey 50 PMs, at least 60% will report spending 30+ minutes per week assembling project status updates manually. | Survey (N=50) | 60% or more report 30+ min/week on status assembly | 2025-04-05 | 2025-04-19 | Completed | Validated | 72% reported 30+ min/week. Median was 45 min. Enterprise PMO segment reported 90+ min. Validates severity of the pain. | Proceed to solution design for this opportunity | E1, E3, E5
EXP-3 | Portfolio visibility without manual assembly | We can reliably aggregate status across 10+ project boards in under 5 seconds | Feasibility | A technical spike can demonstrate cross-board aggregation for 10 boards with 500+ tasks in under 5 seconds response time. | Technical spike (3-day timebox) | Aggregation completes in under 5 seconds for 10 boards / 500 tasks | 2025-04-20 | 2025-04-23 | In Progress |  |  |  | E4

## Kill List
Solution Concept | Opportunity | Date Killed | Reason | Evidence | Experiment IDs | Resurrection Criteria
AI Auto-Status with Task Data Only | Reduce status meeting prep time | 2025-04-15 | Users did not trust summaries that lacked context about WHY tasks were delayed. Task data alone is insufficient. | 3 of 5 users in EXP-1 required significant edits. Missing 'why' context was cited by all 3. | EXP-1 | Revisit if we can integrate communication context (Slack/email) alongside task data to provide 'why' narrative.

## Instructions
EXPERIMENT LOG: Instructions
PURPOSE
Track every experiment you run to validate (or invalidate) assumptions about your product opportunities.
This log creates institutional memory. It prevents re-litigating dead ideas and documents what you learned.
THE EXPERIMENT BRIEF (fill out BEFORE running)
Every experiment starts with these fields filled in before you begin:
Assumption Being Tested: The specific belief that must be true for your solution to work.
Risk Type: Value (will they want it?), Usability (can they use it?), Feasibility (can we build it?), Viability (does the business model work?).
Hypothesis: A falsifiable prediction. Format: 'If [condition], then [measurable outcome].'
Method: How you will test it. Pick the lightest method that answers the question.
Success Criteria: The specific threshold that defines validated vs. invalidated. Set this BEFORE running.
AFTER THE EXPERIMENT
Result: Validated, Invalidated, or Inconclusive. Be honest.
Key Learning: What did you learn? This is often more valuable than the result itself.
Next Action: What do you do with this learning? Iterate, proceed, pivot, or kill.
THE KILL LIST
When you invalidate a solution concept, move it to the Kill List tab.
Include Resurrection Criteria: under what circumstances would you revisit this idea?
The Kill List prevents teams from re-proposing ideas that have already been tested and rejected.